## Sheet1
Comparison of Machine Learning Techniques for Predicting Household Energy Consumption
14321887 - Daniel Musselwhite - psydm7@nottingham.ac.uk
Project Start: 23 September 2020
Week Number:
[6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36
Task | Progress | Time Left | Duration | Start | End | time axis 2020-09-21 to 2021-05-30
Project Proposal Writing | 100% | Complete | 37 days | 2020-09-21 | 2020-10-28
Phase 1 : Preliminary Research
Research suitable ML models, techniques and tools | 100% | Complete | 42 days | 2020-09-30 | 2020-11-11
Research methods to pre-process the data | 100% | Complete | 42 days | 2020-09-30 | 2020-11-11
Research statistical tests and evaluation methods | 100% | Complete | 42 days | 2020-09-30 | 2020-11-11
Research big data approaches | 100% | Complete | 42 days | 2020-09-30 | 2020-11-11
Literature Search | 100% | Complete | 11 days | 2020-09-30 | 2020-10-11
Read + Highlight Literature | 100% | Complete | 10 days | 2020-10-11 | 2020-10-21
Literature Review | 100% | Complete | 21 days | 2020-10-21 | 2020-11-11
Interim Report Writing | 100% | Complete | 16 days | 2020-11-11 | 2020-11-27
Interim Report Editing and Improving | 100% | Complete | 12 days | 2020-11-27 | 2020-12-09
Phase 2 : Main Implementation
2.A : EDA and Cleaning
Analyse the data | 99% | 2 days | 14 days | 2021-01-28 | 2021-02-11
Clean the data | 99% | 2 days | 14 days | 2021-01-28 | 2021-02-11
2.B : Feature engineering and data preparation
Feature engineering | 0% | 16 days | 14 days | 2021-02-11 | 2021-02-25
Prepare data for the models (separate 3D dataset for each meter) | 0% | 16 days | 14 days | 2021-02-11 | 2021-02-25
2.C : Developing RNN Models (for smaller predictions)
Implement and debug the models (RNN, LSTM, GRU, CNN Hybrid) | 0% | 37 days | 21 days | 2021-02-25 | 2021-03-18
(note; models will have to be implemented to predict a smaller problem eg energy usage in days next week based on last 2 weeks)
Validate for optimal hyperparams for models | 0% | 37 days | 14 days | 2021-03-04 | 2021-03-18
(note; cannot use grid search as will have 3428 models, will have to test on a subset of them and average for best hypers)
2.D : Using RNN models iteratively (for the monthly and yearly predictions)
Use model iteratively to get month and yearly predictions | 0% | 51 days | 14 days | 2021-03-18 | 2021-04-01
(Note: Iteratively use models to predict next year then total to give predictions through making prediction on the smaller problem then using those predictions as inputs for the next prediction until have predicted the next 365 days, then aggregating them up to months and yearly values)
Format each models predictions into expected csv structure |  |  | 7 days | 2021-04-01 | 2021-04-08
Get test set score | 0% | 60 days | 2 days | 2021-04-08 | 2021-04-10
(Note: submitting the final formatted csv to competition for it to give us our test set error of total predictions for all meters)
Complete Written Dissertation | 0% | 80 days | 20 days | 2021-04-10 | 2021-04-30
Prepare demo for my project | 0% | 107 days | 7 days | 2021-05-20 | 2021-05-27
(When I find more out more about what I'm doing for each deliverable I will expand them into separate tasks, eg instead of just saying 'demo project')
White Background? (1 = yes, 0 = no) |  |  | 1