## Sheet1
Comparison of Machine Learning Techniques for Predicting Household Energy Consumption
14321887 - Daniel Musselwhite - psydm7@nottingham.ac.uk
Project Start: 23 September 2020
Week Number:
[6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36
Task | Progress | Time Left | Duration | Start | End | time axis 2020-09-21 to 2021-05-30
Project Proposal Writing | 100% | Complete | 37 days | 2020-09-21 | 2020-10-28
Phase 1 : Preliminary Research
Research suitable ML models, techniques and tools | 100% | Complete | 42 days | 2020-09-30 | 2020-11-11
Research methods to pre-process the data | 100% | Complete | 42 days | 2020-09-30 | 2020-11-11
Research statistical tests and evaluation methods | 100% | Complete | 42 days | 2020-09-30 | 2020-11-11
Research big data approaches | 100% | Complete | 42 days | 2020-09-30 | 2020-11-11
Literature Search | 100% | Complete | 11 days | 2020-09-30 | 2020-10-11
Read + Highlight Literature | 100% | Complete | 10 days | 2020-10-11 | 2020-10-21
Literature Review | 100% | Complete | 21 days | 2020-10-21 | 2020-11-11
Interim Report Writing | 100% | Complete | 16 days | 2020-11-11 | 2020-11-27
Interim Report Editing and Improving | 100% | Complete | 12 days | 2020-11-27 | 2020-12-09
Phase 2 : Main Implementation
2.A : EDA and Cleaning
Analyse the data | 100% | Complete | 14 days | 2021-01-28 | 2021-02-11
Clean the data | 100% | Complete | 14 days | 2021-01-28 | 2021-02-11
2.B : Feature engineering and data preparation
Feature engineering | 100% | Complete | 14 days | 2021-02-11 | 2021-02-25
Prepare data for the models (separate 3D dataset for each meter) | 100% | Complete | 14 days | 2021-02-11 | 2021-02-25
2.C : Developing LGBM Models
Implement and debug the LGBM | 100% | Complete | 28 days | 2021-02-25 | 2021-03-25
Modify code to work with clusters | 0% | 11 days | 7 days | 2021-03-25 | 2021-04-01
2.D : Finishing up
Clean and extend/improve the notebooks | 0% | 18 days | 7 days | 2021-04-01 | 2021-04-08
Run the LGBM's and submit the forecasts to receive the test score | 0% | 20 days | 2 days | 2021-04-08 | 2021-04-10
3. Hand in (dissertation and demo)
Complete Written Dissertation | 0% | 40 days | 20 days | 2021-04-10 | 2021-04-30
Prepare demo for my project | 0% | 67 days | 7 days | 2021-05-20 | 2021-05-27
Deadline for dissertation + Code
(When I find more out more about what I'm doing for each deliverable I will expand them into separate tasks, eg instead of just saying 'demo project')
White Background? (1 = yes, 0 = no) |  |  | 1